## Risk Register
Risk register - worked example
The worked example below gives examples of 2 risks for each category.
Category | Description of risk | Impact | Probability | Score before mitigation | Responsibility | Actions to mitigate | Impact after actions | Probability after actions | Revised score
Governance | Failure to recruit and retain sufficient board members | 4 | 3 | 12 | Chair | Succession plan in place Annual recruitment drive Trustee training opportunities | 4 | 1 | 4
Governance | Unmanaged conflicts of interest | 3 | 2 | 6 | Chair | Conflict of interest policy in place Regular training for board and staff Charity governance code adopted | 3 | 1 | 3
Financial | Income more than 10% below budget | 5 | 3 | 15 | CEO | Regular management accounts reviewed by board Implementation of remedial actions identified by board has very high priority Overdraft facility in place to deal with short term cashflow issues | 3 | 2 | 6
Financial | Expenditure more than 10% above budget | 5 | 3 | 15 | CEO | Regular management accounts reviewed by board Procurement policy in place Seek good value contracts which give price security for a number of years Implementation of remedial actions identified by board has very high priority | 3 | 2 | 6
Operational | Serious accident on premises | 5 | 3 | 15 | CEO | Health and safety policy in place and regularly reviewed Significant hazards identified and safety works undertaken Regular staff training on health and safety Insurance policy in place | 3 | 1 | 3
Operational | Failure to recruit to essential posts | 4 | 2 | 8 | CEO | Recruitment process in place including advertising strategy Staff training in place to ensure cover for essential delivery Regular board review of salary levels, terms and conditions | 3 | 1 | 3
Compliance | Failure to make required returns to Companies house, Charity commission, FCA, etc. | 3 | 3 | 9 | Finance Manager | Clear process in place including alerts Oversight by CEO | 3 | 1 | 3
Compliance | Failure to submit required documentation to funders | 5 | 3 | 15 | CEO | Transparent information on terms and conditions of grants and contracts provided to board and senior staff including reporting requirements Oversight by board | 5 | 1 | 5
External | Changes in government policy affecting service delivery | 4 | 2 | 8 | CEO | Monitor proposed changes to give as long as possible to take mitigating action | 4 | 2 | 8
External | Changes in personnel in partner organisations | 3 | 4 | 12 | CEO | Build multiple links within partner organisations Keep in regular contact | 2 | 1 | 2
Asset | Cost of refurbishment works comes in above estimate | 5 | 3 | 15 | CEO | Project costs based on professional assessment Include significant contingency at planning stage | 3 | 2 | 6
Asset | Contractor goes out of business during the build | 5 | 3 | 15 | CEO | Research potential contractors prior to award of contract | 5 | 2 | 10
Specific | Young person is bullied while attending a youth session | 4 | 4 | 16 | CEO | Safeguarding policy in place Safeguarding training for staff and volunteers Anti-bullying message part of all youth work | 4 | 2 | 8
Specific | Staff member threatened or injured during one-to-one advice session | 4 | 4 | 16 | CEO | Health and safety and lone worker policies in place Training on managing difficult situations for all advice workers Triage to identify risky situations Second staff member present during advice session if triage identifies a risk | 4 | 2 | 8

## Explanatory Notes
Explanatory notes
Category of risk | Categories: governance, financial, operational, regulatory and compliance, asset project, external
Description of risk | Details of risk
Impact | The consequences of the risk happening - scored 1-5 (one being very low impact, 5 being very high impact)
Probability | The likelihood of the risk happening scored - 1-5 (one being very low probability, 5 being very high probability)
Score before mitigation | Impact multiplied by probability gives overall risk before actions to mitigate
Responsibility | Who is taking responsibility for managing this risk
Actions to mitigate | What actions are being taken to mitigate risk
Impact after actions | Consequences of risk happening after mitigation - scored 1-5 (one being very low impact, 5 being very high impact)
Probability after actions | Probability that risk will occur after mitigations - 1-5 (one being very low probability, 5 being very high probability)
Score after mitigation | Impact after actions multipkied by probability after actions
Options to deal with risk
Accept | Risks which you cannot anticipate or change need to be accepted - e.g. inflation, changes in Government policy
Transfer | Can the risk be transferred to someone else - e.g. taking out insurance?
Mitigate | Can you take actions to reduce the risk - e.g. health and safety policy, staff training?
Avoid | Can you avoid risk by not doing it? Rarely applies as most risks are fundamental to operation of the organisation.